## Notes
Cowboy Disco Party — September 19, 2026
# | Category | Party Tasks | Status | Assigned | Notes
1 | Theme | Pick Theme | Not Started | Kyle | Includes Name & Dress
2 | Date | Pick Date | Not Started | Kyle | TBD
3 | Theme | Order party favors | Not Started | Kyle/Tammy | TBD
4 | Website | Design Party Website | Not Started | Kyle
5 | Personnel | Hire a party door person | Not Started | Kyle
6 | Personnel | Hire a bartender | Not Started | Kyle
7 | Invite | Design Partiful Invite | Not Started | Kyle | No Maybe Next Time
8 | Invite | Send Partiful Invite | Not Started | Kyle
9 | Invite | Send Partiful Update 1 | Not Started | Kyle
10 | Invite | Send Partiful Update 2 (Food Planning) | Not Started | Jeremy
11 | Invite | Send Final Partiful Update 3 | Not Started | Kyle | Friday night reminder
12 | Games | Design Team Game | Not Started | Kyle/Taylor/Zach | Game design finished
13 | Games | Design Ice Breaker | Not Started | Kyle
14 | Games | Order Prizes | Not Started | Kyle
15 | Games | Pick Up Prizes | Not Started | Kyle
16 | Mains | Pick Out Menu | Not Started | Kyle/Jeremy/Chris
17 | Mains | Pick Up Food 1 | Not Started | Chris
18 | Mains | Pick Up Food 2 | Not Started | Jeremy/Kyle | Scheduled for Friday
19 | Mains | Serving Trays | Not Started | Jeremy/Kyle
20 | Mains | Design Food Signs | Not Started | Kyle
21 | Mains | Print Food Signs | Not Started | Richard | By Saturday
22 | Dessert | Design Dessert | Not Started | Anika
23 | Dessert | Pick Out Desserts | Not Started | Anika/Deborah
24 | Dessert | Serving Trays | Not Started | Jeremy/Kyle | TBD
25 | Drinks/Utensils | Pick Up Ice | Not Started | Kyle/Jeremy/Jeff | Pick up at Fred Meyer
26 | Drinks/Utensils | Pick Up Solo Cups | Not Started | Jeremy/Kyle | Have cups
27 | Drinks/Utensils | Pick Up Napkins | Not Started | Jeremy/Kyle
28 | Drinks/Utensils | Wheel Up Beverage Cart | Not Started | Kyle | Day Of
29 | Drinks/Utensils | Order Utensils | Not Started | Kyle
30 | Decorations | Design Signs | Not Started | Kyle
31 | Decorations | Design Decorations | Not Started | Taylor
32 | Decorations | Print Signs | Not Started | Richard | Day Of
33 | Decorations | Hang Signs | Not Started | Kyle | Day Of
34 | Music | Design Set | Not Started | Hunter
35 | Music | Set Up | Not Started | Hunter
36 | Music | Set Tear Down | Not Started | Crew
37 | Cleaning | Pick Up Trash Bags | Not Started | Kyle
38 | Cleaning | Print Bathroom Signs | Not Started | Kyle | Day Of
39 | Photos | Centralized Photo Share | Not Started | Kyle | Part of central website
40 | Feedback | Debrief | Not Started | Kyle
41 | Feedback | Questionnaire | Not Started | Kyle

## Schedule
Timing
Day | Time | Action
Friday | 5:00 | Pick up food
Friday | 6:30 | Prep food
Friday | 6:30 | Prep signs
Saturday | 9:00 | Print signs
Saturday | 17:00 | Hang signs
Saturday | 17:30 | Wheel up bar cart
Saturday | 6:30 | Party Start
Saturday | 7:30 | Ice Breaker
Saturday | 8:15 | Game
Saturday | 8:30 | Costume Contest
Saturday | 8:35 | Group Photo
Saturday | TBD | Sunset
Saturday | 10:00 | Party Ends

## Signs
Sign List
QR Party Code | 1
Entrance | 1
4th Ave Entrance | 1
Street Entrance | 1
Cowboy Disco Saloon | 1
Food Signs | 2
Drink Sign | 1

## Committe
Party Planning Committee
Tasks
Kyle | Lead
Jeremy | Food
Richard | Logistics
Chris | Food/Setup
Cass | Planning
Tammy | Theme/Decorations
Taylor | Game